## GuideMe
GuideMe
| Proje Başlangıç Tarihi | 2023-02-27 |  |  | İlk | Hafta | 1 |  | Hafta 1 | [6 empty] | Hafta 2 | [6 empty] | Hafta 3 | [6 empty] | Hafta 4 | [6 empty] | Hafta 5 | [6 empty] | Hafta 6 | [6 empty] | Hafta 7 | [6 empty] | Hafta 8 | [6 empty] | Hafta 9 | [6 empty] | Hafta 10 | [6 empty] | Hafta 11 | [6 empty] | Hafta 12 | [6 empty] | Hafta 13 | [6 empty] | Hafta 14
| Proje Yöneticisi | Firdevs Nur Açıkgöz | [6 empty] | 2023-02-27 | [6 empty] | 2023-03-06 | [6 empty] | 2023-03-13 | [6 empty] | 2023-03-20 | [6 empty] | 2023-03-27 | [6 empty] | 2023-04-03 | [6 empty] | 2023-04-10 | [6 empty] | 2023-04-17 | [6 empty] | 2023-04-24 | [6 empty] | 2023-05-01 | [6 empty] | 2023-05-08 | [6 empty] | 2023-05-15 | [6 empty] | 2023-05-22 | [6 empty] | 2023-05-29
 | time axis 2023-02-27 to 2023-06-04
İK | İş Paketleri ve Görevler | Sorumlu | PREDECESSOR | Başlangıç | Bitiş | Süre | Tam. Oranı | Fili Gün | time axis 2023-02-27 to 2023-06-04
1 | Proje Başlatma Aşaması | Firdevs Nur Açıkgöz |  | 2023-02-27 | 2023-03-15 | 17 | 100% | 13
1.1 | Projee Ekibi Oluşturma | Firdevs Nur Açıkgöz |  | 2023-02-27 | 2023-03-02 | 4 | 100% | 4
1.2 | Proje Fikri ve Alternatiflerinin Belirlenmesi | Firdevs Nur Açıkgöz |  | 2023-03-03 | 2023-03-05 | 3 | 100% | 1
1.3 | Projenin Konusunun Belirlenmesi | Firdevs Nur Açıkgöz |  | 2023-03-06 | 2023-03-08 | 3 | 100% | 3
1.4 | Proje Beyanı Hazırlama | Firdevs Nur Açıkgöz |  | 2023-03-08 | 2023-03-13 | 6 | 100% | 4
1.5 | Ön Fizibilite Çalışması | Firdevs Nur Açıkgöz |  | 2023-03-09 | 2023-03-15 | 7 | 100% | 5
1.5.1 | Fizibilite Alanlarının Değerlendrilmesi | Firdevs Nur Açıkgöz |  | 2023-03-10 | 2023-03-12 | 3 | 100% | 1
1.5.2 | Genel Fizibilite Kararının Alınması | Firdevs Nur Açıkgöz |  | 2023-03-12 | 2023-03-15 | 4 | 100% | 3
2 | Planlama | Elifnur Yürümez |  | 2023-03-16 | 2023-03-28 | 13 |  | 9
2.1 | İş Paketlerinin Belirlenmesi | Elifnur Yürümez |  | 2023-03-16 | 2023-03-17 | 2 | 100% | 3
2.2 | Görevlerin Belirlenmesi ve Dağılımlarının Yapılması | Elifnur Yürümez |  | 2023-03-18 | 2023-03-21 | 4 | 100% | 2
2.2.1 | Görevlerin Belirlenmesi | Elifnur Yürümez |  | 2023-03-18 | 2023-03-19 | 2 | 100% | 4
2.2.2 | Gerekli Değişiklerin Yapılması ve Onaylanması | Elifnur Yürümez |  | 2023-03-20 | 2023-03-21 | 2 | 100% | 2
2.3 | İş Kırlımının Görselleştirilmesi | Firdevs Nur Açıkgöz |  | 2023-03-22 | 2023-03-24 | 3 | 100% | 3
2.4 | İş Çizelgelerinin Belirlenmesi | Elifnur Yürümez |  | 2023-03-24 | 2023-03-28 | 5 | 100% | 3
2.4.1 | Gantt Şeması Oluşturma | Elifnur Yürümez |  | 2023-03-24 | 2023-03-28 | 5 | 100% | 3
3 | Analiz | Elifnur Yürümez |  | 2023-03-29 | 2023-04-25 | 28 |  | 20
3.1 | Gereksinim Analizi | Elifnur Yürümez |  | 2023-03-29 | 2023-04-07 | 10 | 0% | 8
3.1.1 | Piyasayı Analiz Etme | Mert Tayanç |  | 2023-03-29 | 2023-04-03 | 6 | 0% | 4
3.1.1.1 | Hedef Kitlenin Belirlenmesi | Mert Tayanç |  | 2023-04-04 | 2023-04-06 | 3 | 0% | 3
3.1.2 | Gereksinim Listesi OLuşturma | Elifnur Yürümez |  | 2023-04-07 | 2023-04-11 | 5 | 0% | 3
3.2 | Süreç Modelleme | Elifnur Yürümez, Sude Saka |  | 2023-04-12 | 2023-04-16 | 5 | 0% | 3
3.2.1 | Gereksinim Listesi Analizi | Elifnur Yürümez |  | 2023-04-07 | 2023-04-13 | 7 | 0% | 5
3.2.2 | Veri Akış Diyagramlarının Hazırlanması | Sude Saka |  | 2023-04-13 | 2023-04-15 | 3 | 0% | 2
3.2.2.1 | Bağlam Diyagramı | Sude Saka |  | 2023-04-13 | 2023-04-15 | 3 | 0% | 2
3.3 | Veri Modelleme | Sude Saka, Artuğ Akbulut |  | 2023-04-16 | 2023-04-20 | 5 | 0% | 4
3.3.1 | Veri Akış Diyagramlarının İncelenmesi | Sude Saka |  | 2023-04-17 | 2023-04-19 | 3 | 0% | 3
3.3.2 | Veri Sözlüklerinin Oluşturulması | Sude Saka |  | 2023-04-19 | 2023-04-21 | 3 | 0% | 3
3.4 | Mantık Modelleme | Artuğ Akbulut |  | 2023-04-22 | 2023-04-25 | 4 | 0% | 2
3.4.1 | Sözde Kod Tasarımı | Artuğ Akbulut |  | 2023-04-22 | 2023-04-25 | 4 | 0% | 2
3.4.2 | Karar Tablosu Tasarımı | Artuğ Akbulut |  | 2023-04-22 | 2023-04-25 | 4 | 0% | 2
3.4.3 | Karar Ağacı Tasarımı | Artuğ Akbulut |  | 2023-04-22 | 2023-04-24 | 3 | 0% | 1
3.4.3.1 | Alternatif Kararları Seçme | Sude Saka, Elifnur Yürümez |  | 2023-04-24 | 2023-04-25 | 2 | 0% | 2
4 | Tasarım Aşaması |  |  | 2023-04-26 | 2023-05-09 | 14 | 0% | 10
4.1 | Uygulama Tasarımı | Sude Saka, Artuğ Akbulut |  | 2023-04-26 | 2023-04-30 | 5 | 0% | 3
4.2 | İnsan Bilgisayar Etkileşimi | Elifnur Yürümez |  | 2023-04-30 | 2023-05-02 | 3 | 0% | 2
4.2.1 | Sistem ve Gerçek dünyanın Uyumu Testi | Elifnur Yürümez |  | 2021-04-30 | 2021-05-01 | 2 | 0%
4.2.1.1 | Uyum Testinin Değerlendirilmei ve Analizi | Elifnur Yürümez |  | 2023-05-02 | 2023-05-02 | 1 | 0% | 1
4.2.2 | Kullanıcı Kontrolü ve Özgürlüğü Analizi | Elifnur Yürümez |  | 2023-04-30 | 2023-05-01 | 2 | 0% | 1
4.2.3 | Kullanıcı ile Zevkli ve Riayetli Bir İletişim | Elifnur Yürümez |  | 2023-04-30 | 2023-05-01 | 2 | 0% | 1
4.3 | Arayüz Tasarımı | Firma |  | 2023-04-26 | 2023-04-29 | 4 | 0% | 3
4.4 | Veri Tabanı Tasarımı | Sude Saka, Artuğ Akbulut |  | 2023-05-01 | 2023-05-09 | 9 | 0% | 7
4.4.1 | Gerekli Bigilerin Bulma ve Düzenleme | Sude Saka, Artuğ Akbulut |  | 2023-05-01 | 2023-05-04 | 4 | 0% | 4
4.4.2 | Bilgileri Tablolara Bölme | Sude Saka, Artuğ Akbulut |  | 2023-05-05 | 2023-05-09 | 5 | 0% | 3
5 | Prototip Uygulama | Sude Saka, Artuğ Akbulut |  | 2023-05-09 | 2023-05-26 | 18 |  | 14
5.1 | Prototip UygulamayıTest Etme | Sude Saka, Artuğ Akbulut |  | 2023-05-09 | 2023-05-18 | 10 | 0% | 8
5.1.1 | Test Sonuçlarını Analiz Etme | Elifnur Yürümez |  | 2023-05-11 | 2023-05-18 | 8 | 0% | 6
5.2 | Uygulama Üzerinde İyileştirmeler Yapma | Sude Saka, Artuğ Akbulut |  | 2023-05-19 | 2023-05-24 | 6 | 0% | 4
5.3 | Uygulamayı Piyasaya Hazır Hale Getirmek | Sude Saka, Artuğ Akbulut |  | 2023-05-25 | 2023-05-26 | 2 | 0% | 2
6 | Proje Sonlandırma | Firdevs Nur Açıkgöz |  | 2023-05-26 | 2023-06-04 | 10 |  | 6
6.1 | Proje Dosyası Hazırlama | Firdevs Nur Açıkgöz |  | 2023-05-27 | 2023-06-02 | 7 | 0% | 5
6.1.1 | İçindekiler Kısmını Oluşturma | Firdevs Nur Açıkgöz |  | 2023-05-27 | 2023-05-28 | 2 | 0% | 0
6.1.2 | Doküman Güncelleme | Firdevs Nur Açıkgöz |  | 2023-05-29 | 2023-05-30 | 2 | 0% | 2
6.1.3 | Doküman Birleştirme | Firdevs Nur Açıkgöz |  | 2023-05-30 | 2023-06-02 | 4 | 0% | 4
6.2 | Uygulamayı Kullanıcıya Sunma | Firdevs Nur Açıkgöz |  | 2023-06-03 | 2023-06-04 | 2 | 0% | 0
Şablon
Lütfen Help sayfasını okuyarak kullanım yardımı alınız.
1 | [ Seviye 1 - İş Paketi ] |  |  |  | - |  |  | -
1.1 | . [Seviye 2 - İş ] |  |  |  | - |  |  | -
1.1.1 | . . [ Seviye 3 - Görev ] |  |  |  | - |  |  | -
1.1.1.1 | . . . [ Seviye 4 Alt Görev ] |  |  |  | - |  |  | -
1.1.1.1.1
Note on A7: Work Breakdown Structure Level 1: 1, 2, 3, ... Level 2: 1.1, 1.2, 1.3, ... Level 3: 1.1.1, 1.1.2, 1.1.3, … - The WBS uses a formula to control the numbering, but the formulas are different for different levels. Copy and Paste the cells in the WBS column from the examples at the bottom of the worksheet.
Note on B7: Task Description Enter the name of each task and sub-task. Use indents for sub-tasks.
Note on C7: Task Lead Enter the name of the Task Lead in this column.
Note on D7: Predecessor Tasks: You can use this column to enter the WBS of a predecessor for reference. The PRO version uses formulas to automatically calculate the Start Date based on the Predecessor.
Note on E7: Task Start Date You can manually enter the Start Date for each task or use a formula to create a dependency on a Predecessor. For example, you could enter =enddate+1 to set the Start date to the next calendar day, or =WORKDAY(enddate,1) to set the Start date to the next work day (excluding weekends), where enddate is the cell reference for the End date of the Predecessor task.
Note on F7: End Date: The End Date is calculated based on the Start Date and the Calendar Days columns.
Note on G7: Duration (Calendar Days) The duration is the number of calendar days for the given task. The duration is calculated as the End Date minus the Start Date plus 1 day, so that a task starting and ending on the same day has a duration of 1 day. Note: The conditional formatting used to create the gantt chart references this column.
Note on H7: Percent Complete Update the status of this task by entering the percent complete (between 0% and 100%).
Note on I7: Work Days Counts the number of work days, excluding the weekends (Saturday and Sunday). In the PRO version, you can customize the work week and list specific non-working days like holidays. In the PRO version, the default input is the Work Days instead of the Calendar Days.